## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Manual Data Entry | As a user, I want to manually input different types of income and expenses (e.g., food, clothing) so that I can accurately track my financial activities. | Must have | 1 | Verify all input fields (amount, category, date) are functional. Ensure data persists after saving. | / | 2025-04-04 | 2025-04-15
2 | Calendar Integration | As a mother, I want to view and edit daily income/expenses directly on a calendar so that I can easily track financial activities by date. | Must have | 1 | Verify calendar displays entries with correct dates. | / | 2025-04-04 | 2025-04-15
3 | Budget Management | As a student, I want to set daily/monthly budgets and view remaining balances so that I can control my spending habits. | Must have | 1 | Verify budget calculations (daily/monthly). Ensure alerts trigger when exceeding budgets. | / | 2025-04-04 | 2025-04-15
4 | Wishlist | As a child, I want to create a wishlist for desired purchases so that I can plan my expenses more effectively. | Could have | 3 | Verify items can be added/removed from the wishlist. Link wishlist items to budget goals. | / | 2025-05-01 | 2025-05-15
5 | Photo OCR Import | As a user, I want to import bills via photo OCR to automatically categorize transactions so that I can reduce manual data entry. | Should have | 2 | Verify OCR accurately extracts amount, category, and date. Support common receipt formats. | / | 2025-04-16 | 2025-04-30
6 | Multi-Currency | As a traveler, I want to track expenses in multiple currencies so that I can manage international transactions seamlessly. | Could have | 3 | Verify real-time currency conversion. Allow manual adjustment of exchange rates. | / | 2025-05-01 | 2025-05-15
7 | AI Budget Advice | As a user, I want AI-driven budget recommendations based on spending history so that I can optimize my financial planning. | Want to have | 4 | Verify AI generates actionable insights (e.g., "Reduce dining-out expenses by 20%"). Ensure recommendations align with user goals. | / | 2025-05-16 | 2025-05-20
8 | Shared Ledger | As a family member, I want to collaborate on a shared ledger with others so that we can collectively manage household finances. | Should have | 2 | Verify multi-user access and synchronization. Ensure conflict resolution for simultaneous edits. | / | 2025-04-16 | 2025-04-30
9 | Multi-Ledger Management | As a user, I want to create and manage multiple ledgers (e.g., personal life, business operations) for different scenarios so that I can separate and track finances clearly. | Must have | 1 | Verify users can create/switch ledgers. Ensure data isolation between ledgers. | / | 2025-04-04 | 2025-04-15
10 | External Login Integration | As a developer, I want the system to support external login methods so that I can integrate various login options. | Could have | 3 | The system successfully integrates external login methods and supports logins from mainstream platforms. | / | 2025-05-01 | 2025-05-15
11 | API Documentation | As a developer, I want clear API documentation so that I can quickly understand and use the system's interfaces. | Should have | 2 | API documentation is comprehensive, accurate, and includes examples for all endpoints. | / | 2025-04-16 | 2025-04-30
12 | Code Review Process | As a developer, I want an efficient code review process so that I can promptly identify and fix issues in the code. | Should have | 2 | The code review process is well-defined, provides quick feedback, and tracks review outcomes. | / | 2025-04-16 | 2025-04-30
13 | Automated Regression Testing | As a tester, I want to automate regression testing so that I can reduce the time spent on manual verification. | Must have | 1 | Automated test scripts cover core functionalities and generate reports automatically. | / | 2025-04-04 | 2025-04-15
14 | Automated Regression Testing | As a tester, I want a centralized defect tracking system so that I can effectively record and track issues found during testing. | Should have | 2 | The defect tracking system updates issues in real-time and supports team collaboration. | / | 2025-04-16 | 2025-04-30
15 | Test Report Generation | As a tester, I want to easily generate test reports so that I can present testing results and system quality to the team and management. | Could have | 3 | Test report templates are standardized and include results, analysis, and recommendations. | / | 2025-05-01 | 2025-05-15
16 | One-Click Rollback | As a technical engineer, I want one-click rollback to the previous version so that I can quickly fix production environment failures. | Must have | 1 | The production environment has a one-click rollback feature that can be activated during failures. | / | 2025-04-04 | 2025-04-15
17 | Automated Deployment Pipeline | As a technical engineer, I want an automated deployment pipeline so that I can rapidly and reliably deploy code to different environments. | Must have | 1 | The deployment pipeline is automated, supports multiple environments, and monitors deployment status in real-time. | / | 2025-04-04 | 2025-04-15
18 | Referral Link for Content Sharing | As a marketing team, I want that users can generate promotional links when sharing content, in order to track conversion rates and conduct precise marketing. | Must have | 2 | Ensure that the generated promotional links can accurately track user clicks and conversions. | / | 2025-04-16 | 2025-04-30
19 | Cycle accounting automation | As an operations team, I want to reduce repetitive user actions in order to lower the volume of customer service inquiries | Should have | 2 | Ensure support for setting fixed income and expenses on a monthly/weekly basis | / | 2025-04-16 | 2025-04-30
20 | Multi currency accounting | As an international business team, I want to support multiple currencies such as USD/EUR in order to expand into overseas markets. | Could have | 3 | Ensure real-time exchange rate automatic conversion. | / | 2025-05-01 | 2025-05-15
21 | Consumer Trend Report | As a marketing team, I need to analyze high-frequency categories of user consumption (such as catering and transportation) in order to accurately advertise. | Must have | 1 | Ensure automatic generation of monthly consumption TOP5 categories, with data updated daily. | / | 2025-04-04 | 2025-04-15
22 | User fission mechanism | As a marketing team, I want old users to recommend new users in order to reduce customer acquisition costs. | Could have | 3 | Ensure to provide an invitation reward mechanism, such as inviting 1 person to register for a 10 yuan coupon. | / | 2025-05-01 | 2025-05-15
23 | Free trial mechanism | As a sales team, I want to have membership trial services so that new customers can quickly convert after trial, in order to increase transaction rates. | Could have | 3 | Ensure the provision of a trial membership mechanism for new users, such as a 15 day free trial period. | / | 2025-05-01 | 2025-05-15
24 | Multi ledger function | As a sales team, I want to provide multi ledger accounting functionality to meet the needs of enterprise or individual users to manage multiple project ledgers and increase user base. | Must have | 1 | Ensure the ability to manage multiple ledgers simultaneously and transfer funds between them. | / | 2025-04-04 | 2025-04-15
25 | Compliance of data processing | As a legal department, I want our application can fully comply with GDPR privacy regulations to ensure the protection of all users' personal data. | Must have | 1 | Ensure that the processing flow of user data complies with GDPR requirements and provides privacy settings options. | / | 2025-04-04 | 2025-04-15
26 | Terms and Conditions Agreement | As a legal department, I want that users can clearly agree to the terms and conditions when using our product to prevent legal disputes and protect the company's rights and interests. | Must have | 1 | Ensure that users agree and confirm to read the terms and privacy policy during the registration and usage process. | / | 2025-04-04 | 2025-04-15
27 | Open API for Extension Development | As a third-party developer, I hope the accounting app can provide an open and well-documented API interface so that I can develop extended functions, such as integrating with specific financial services or creating personalized data analysis plugins, to enrich the app's functionality. | Must have | 1 | The API documentation is complete and clear. At least two types of extended functions can be successfully integrated. Technical support responds within 24 hours. | / | 2025-04-04 | 2025-04-15
28 | Clear Data Interaction Specification | As a third-party developer, I expect the accounting app to clarify data interaction specifications and offer technical support for the efficient integration of developed functions. | Must have | 1 | The specification document covers key information. There are no major obstacles during integration. Technical support responds within 4 hours. | / | 2025-04-04 | 2025-04-15
29 | Precision Marketing Collaboration | As a partner, I hope the accounting app can provide accurate user profiles and marketing channels based on users' consumption data to enable personalized marketing. | Must have | 1 | The user profiles are accurate. Sales increase by over 15% after marketing activities. | / | 2025-04-04 | 2025-04-15
30 | Joint Brand Promotion | As a partner, I look forward to conducting joint brand promotion activities with the accounting app, such as displaying brand logos and launching co-branded events, to enhance the brand awareness of both parties. | Should have | 2 | The brand logo is displayed in the app. The co - branded event has over 200 participants. Brand awareness increases by 10% after the event. | / | 2025-04-16 | 2025-04-30
31 | Compliance Audit Log Support | As a member of the legal/compliance team, I hope the accounting app has a comprehensive log system to record the entire data-processing process for compliance audits. | Must have | 1 | Logs cover all aspects of data handling. Data is accurate, complete, and retrievable. There are no log - related issues during audits. | / | 2025-04-04 | 2025-04-15
32 | Policy Update Synchronization | As a member of the legal/compliance team, I expect the accounting app to establish a synchronization mechanism with legal and policy updates and adjust business processes in a timely manner. | Should have | 2 | Adjustment process starts within 7 days after policy updates. Adjusted processes meet new policy requirements. | / | 2025-04-16 | 2025-04-30
33 | Security Vulnerability Reporting Channel | As a security professional, I hope the accounting app can set up a security vulnerability feedback channel for timely reporting to enhance app security. | Must have | 1 | The feedback channel is convenient. The development team responds within 2 hours after reporting. The vulnerability repair rate reaches over 90%. | / | 2025-04-04 | 2025-04-15
34 | Regular Security Training and Information Sharing | As a security professional, I expect the accounting app to provide regular security training and share the latest security threat information. | Should have | 2 | Training is provided at least once every 3 months. Information is timely and targeted. Training satisfaction reaches over 80%. | / | 2025-04-16 | 2025-04-30
35 | Updated Style Guide | As a UI designer, I hope the accounting app can regularly update the style guide to clarify interface design specifications and help me create a beautiful and consistent interface. | Should have | 2 | The style guide is updated every 3 months at most. The designed interface scores over 80 points in internal reviews. | / | 2025-04-16 | 2025-04-30
36 | User Interface Optimization Feedback | As a UI designer, I expect to receive user feedback on the existing interface to optimize the design. | Must have | 1 | At least 50 valid feedbacks are collected monthly. The operation convenience score improves by over 10 points after optimization. | / | 2025-04-04 | 2025-04-15
37 | User Behavior Data Collection Permission | As a user experience researcher, I hope the accounting app can grant me permission to collect user behavior data to analyze user behavior and discover user needs. | Must have | 1 | Permission for data collection is obtained. Data is complete and accurate. At least 3 optimizable issues are found through analysis. | / | 2025-04-04 | 2025-04-15
38 | User Feedback Integration Mechanism | As a user experience researcher, I expect the accounting app to establish a user feedback integration mechanism to comprehensively understand user opinions and drive product optimization. | Must have | 1 | The mechanism covers at least 3 feedback channels. Feedback is processed within 3 days. User satisfaction increases by over 10% after optimization. | / | 2025-04-04 | 2025-04-15
39 | Privacy Data Breach Prevention | As a maintenance personnel, I want to immediately block connections and notify the security team when there are abnormal access attempts to 'user passwords' or 'facial recognition' data. | Must have | 2 | 1. Detect multiple password attempts from the same IP address. 2. Trigger account lockout and record device fingerprint. | Related to Secondary Function 3 (Password Protection) | 2025-04-16 | 2025-04-30
40 | Operation Log Access for Support | As a technical support staff, I want to access user operation logs to quickly diagnose issues related to manual and automatic data input of various types of expenses and income. | Must have | 1 | 1. Ability to filter logs by user ID 2. Logs include timestamps, input methods, and data categories | Core Function 1 (Data Input) | 2025-04-04 | 2025-04-15
41 | System Resource Monitoring | As maintenance personnel, I want to monitor system resources such as CPU and memory usage to proactively manage system performance and prevent downtime. | Must have | 2 | 1. Real-time monitoring dashboards 2. Alerts when resource usage exceeds 80% | / | 2025-04-16 | 2025-04-30
42 | Backup and Restore Logs | As maintenance personnel, I want detailed logs of backup and restore operations to ensure data recovery processes are functioning correctly. | Must have | 1 | 1. Log backup start and end times 2. Record any errors during the process | Data Integrity Maintenance | 2025-04-04 | 2025-04-15
43 | User Activity Monitoring | As a technical support staff, I want to monitor user activities to detect unusual behavior that may indicate security issues or system misuse. | Could have | 1 | 1. Track login times and IP addresses 2. Alert on multiple failed login attempts | Security Monitoring | 2025-04-04 | 2025-04-15
44 | Historical Data Management for AI Trend Analysis | As a maintenance personnel, I want to move bill data older than 3 years to cold storage, so that the AI trend prediction feature, which analyzes data from the past year, has a manageable and efficient database. | Could have | 2 | Queries for cold storage data should have an acceptable delay of no more than 5 seconds. Data migration tasks should be performed during off-peak business hours to minimize impact on system performance. | This user story relates to the least important feature 1 (AI trend analysis). | 2025-04-16 | 2025-04-30
45 | Batch Operation Monitoring | As a maintenance personnel, I want to monitor batch processing operations to prevent data loss caused by incorrect operations. | Must have | 1 | Record high-risk operations such as batch deletions. Send an alert when the number of batch operations exceeds a certain threshold. | / | 2025-04-04 | 2025-04-15
46 | Server Performance Monitoring | As a maintenance personnel, I want to monitor server performance metrics in real-time to ensure system stability when processing large amounts of account book data. | Must have | 1 | Real-time display of CPU, memory, and disk usage. Send alerts when metrics exceed predefined thresholds. | / | 2025-04-04 | 2025-04-15
47 | External Login Integration | As a developer, I want the system to support external login methods so that I can integrate various login options. | Could have | 3 | The system successfully integrates external login methods and supports logins from mainstream platforms. | / | 2025-05-01 | 2025-05-15
48 | API Documentation | As a developer, I want clear API documentation so that I can quickly understand and use the system's interfaces. | Should have | 2 | API documentation is comprehensive, accurate, and includes examples for all endpoints. | / | 2025-04-16 | 2025-04-30
49 | Code Review Process | As a developer, I want an efficient code review process so that I can promptly identify and fix issues in the code. | Should have | 2 | The code review process is well-defined, provides quick feedback, and tracks review outcomes. | / | 2025-04-16 | 2025-04-30
50 | Automated Regression Testing | As a tester, I want to automate regression testing so that I can reduce the time spent on manual verification. | Must have | 1 | Automated test scripts cover core functionalities and generate reports automatically. | / | 2025-04-04 | 2025-04-15
51 | Automated Regression Testing | As a tester, I want a centralized defect tracking system so that I can effectively record and track issues found during testing. | Should have | 2 | The defect tracking system updates issues in real-time and supports team collaboration. | / | 2025-04-16 | 2025-04-30
52 | Test Report Generation | As a tester, I want to easily generate test reports so that I can present testing results and system quality to the team and management. | Could have | 3 | Test report templates are standardized and include results, analysis, and recommendations. | / | 2025-05-01 | 2025-05-15
53 | One-Click Rollback | As a technical engineer, I want one-click rollback to the previous version so that I can quickly fix production environment failures. | Must have | 1 | The production environment has a one-click rollback feature that can be activated during failures. | / | 2025-04-04 | 2025-04-15
54 | Automated Deployment Pipeline | As a technical engineer, I want an automated deployment pipeline so that I can rapidly and reliably deploy code to different environments. | Must have | 1 | The deployment pipeline is automated, supports multiple environments, and monitors deployment status in real-time. | / | 2025-04-04 | 2025-04-15
55 | Privacy Data Breach Prevention | As a maintenance personnel, I want to immediately block connections and notify the security team when there are abnormal access attempts to 'user passwords' or 'facial recognition' data. | Must have | 2 | 1. Detect multiple password attempts from the same IP address. 2. Trigger account lockout and record device fingerprint. | Related to Secondary Function 3 (Password Protection) | 2025-04-16 | 2025-04-30
56 | Operation Log Access for Support | As a technical support staff, I want to access user operation logs to quickly diagnose issues related to manual and automatic data input of various types of expenses and income. | Must have | 1 | 1. Ability to filter logs by user ID 2. Logs include timestamps, input methods, and data categories | Core Function 1 (Data Input) | 2025-04-04 | 2025-04-15
57 | System Resource Monitoring | As maintenance personnel, I want to monitor system resources such as CPU and memory usage to proactively manage system performance and prevent downtime. | Must have | 2 | 1. Real-time monitoring dashboards 2. Alerts when resource usage exceeds 80% | / | 2025-04-16 | 2025-04-30
58 | Backup and Restore Logs | As maintenance personnel, I want detailed logs of backup and restore operations to ensure data recovery processes are functioning correctly. | Must have | 1 | 1. Log backup start and end times 2. Record any errors during the process | Data Integrity Maintenance | 2025-04-04 | 2025-04-15
59 | User Activity Monitoring | As a technical support staff, I want to monitor user activities to detect unusual behavior that may indicate security issues or system misuse. | Could have | 1 | 1. Track login times and IP addresses 2. Alert on multiple failed login attempts | Security Monitoring | 2025-04-04 | 2025-04-15
60 | Historical Data Management for AI Trend Analysis | As a maintenance personnel, I want to move bill data older than 3 years to cold storage, so that the AI trend prediction feature, which analyzes data from the past year, has a manageable and efficient database. | Could have | 2 | Queries for cold storage data should have an acceptable delay of no more than 5 seconds. Data migration tasks should be performed during off-peak business hours to minimize impact on system performance. | This user story relates to the least important feature 1 (AI trend analysis). | 2025-04-16 | 2025-04-30
61 | Batch Operation Monitoring | As a maintenance personnel, I want to monitor batch processing operations to prevent data loss caused by incorrect operations. | Must have | 1 | Record high-risk operations such as batch deletions. Send an alert when the number of batch operations exceeds a certain threshold. | / | 2025-04-04 | 2025-04-15
62 | Server Performance Monitoring | As a maintenance personnel, I want to monitor server performance metrics in real-time to ensure system stability when processing large amounts of account book data. | Must have | 1 | Real-time display of CPU, memory, and disk usage. Send alerts when metrics exceed predefined thresholds. | / | 2025-04-04 | 2025-04-15